## Summary
Sikka Wallet — QA Bug Report
Consolidated QA Findings — Sikka Wallet Platform
Report Scope:
• Sikka Wallet Web Application — Admin Panel (platform-wide administration)
• Sikka Wallet Web Application — Owner Portal (shop owner dashboard, staff, cards, customers)
• Sikka Wallet Main Website (public marketing site)
• Loyal Sikka App (mobile app used by Manager/Scanner/Shop roles to issue and manage loyalty cards)
• Sikka Wallet App — customer-facing app used for scanning and viewing card/reward details (no bugs reported yet; included here for scope tracking)
Total Confirmed Bugs |  | 169
By Application/Module Area
Application | Count
Sikka Wallet Web App — Admin Panel | 57
Sikka Wallet Web App — Owner Portal | 50
Sikka Wallet Main Website | 15
Loyal Sikka App | 47
By Priority
Priority | Count
High | 68
Medium | 77
Low | 24
Note:
This is a new, separate project from the Onzo bug tracker. Bug IDs use the SW- prefix for the Admin/Owner/Main Website report and LSA- prefix for the Loyal Sikka App report, matching each source document's own numbering. The Sikka Wallet customer app (scanning + card details) has no bugs logged yet and is listed for scope awareness only.

## Admin Panel
Bug ID | Module/Area | Title | Priority | Status | Description
SW-001 | Targets Page | Missing Action Column and Icons | Medium | To Do | The Targets page was missing the required Action column and action icons for managing target records.
SW-002 | Targets Page | Edit Action Does Not Return to Main Table | Medium | To Do | After editing and saving a target, the system did not navigate back to the main targets table.
SW-003 | Targets Page | CTA Needs Improvement | Medium | To Do | The CTA buttons on the Targets page require UI and usability improvements.
SW-004 | Targets Page | New Target Form UI Issues | Medium | To Do | The New Target form contains UI inconsistencies and requires design fixes.
SW-005 | Leads Page | Missing Quick CTA Filters | Medium | To Do | Quick CTA buttons for filters are missing on the Leads page, reducing filtering efficiency.
SW-006 | Agents Page | Missing Action Column | High | To Do | The Agents table is missing an Action column and related action icons required for record management.
SW-007 | Agents Page | New Agent Form UI Issues | Medium | To Do | The New Agent form appears in the center of the screen and does not follow the intended design layout.
SW-008 | Agents Page | Slow CTA Response | Medium | To Do | CTA buttons on the Agents page respond slowly and require optimization.
SW-009 | Agents Page | Edit Action Does Not Return to Main Table | Medium | To Do | After editing and saving an agent, the system does not navigate back to the main table view.
SW-010 | Commission Page | Table Column Alignment Issue | Medium | To Do | One or more table columns are misaligned, causing content to appear in incorrect positions.
SW-011 | Shop Page | Missing Action Column | High | To Do | The Shop table is missing an Action column and action icons for managing records.
SW-012 | Shop Page | New Shop Form UI Issues | Medium | To Do | The New Shop form contains UI inconsistencies and requires design improvements.
SW-013 | Shop Page | Back to Shop Button Issue | Medium | To Do | The "Back to Shop" button does not function consistently and requires fixing across the website.
SW-014 | Shop Page | Slow CTA Response | Medium | To Do | CTA buttons on the Shop page are slow to respond.
SW-015 | Shop Page | Edit Action Does Not Return to Main Table | Medium | To Do | After editing and saving a shop record, the system does not return to the main table.
SW-016 | Card Templates Page | New Template Button Not Working | High | To Do | The New Template button is not functioning as expected.
SW-017 | Card Templates Page | Missing Action Column and CTA Issues | Medium | To Do | Action column/icons are missing and CTA functionality requires improvement.
SW-018 | Plans Page | New Plans Form UI Issues | Medium | To Do | The New Plans form requires UI fixes to match the expected design.
SW-019 | Plans Page | Missing Action Column | High | To Do | The Plans table is missing an Action column and action icons.
SW-020 | Plans Page | Slow CTA Response | Medium | To Do | CTA buttons on the Plans page respond slowly.
SW-021 | Invoice Page | New Invoice Form UI Issues | Medium | To Do | The New Invoice form requires UI improvements and design fixes.
SW-022 | Invoice Page | Payment Reference Actions Empty | High | To Do | The Payment Reference actions menu is empty and does not provide any actionable options.
SW-023 | Dashboard | Manage Button UI Needs Improvement | Medium | To Do | The Manage button on the Dashboard does not follow the overall design standards and requires UI improvement.
SW-024 | Statistics Page | Graph Not Displaying | High | To Do | The graph section on the Statistics page does not appear, preventing users from viewing statistical data.
SW-025 | Agents Page | New Agent Form UI Issues | Medium | To Do | The New Agent form requires UI adjustments to its positioning and layout.
SW-026 | Commission Page | Table Layout Issue | Medium | To Do | The Commission table contains alignment and positioning issues that require correction.
SW-027 | Shop Page | New Shop Form UI Issues | Medium | To Do | The New Shop form requires UI improvements.
SW-028 | Card Templates Page | New Template Button Requires Fix | Medium | To Do | The New Template button requires UI and functionality fixes.
SW-029 | Plans Page | New Plans Form Requires Fixes | Medium | To Do | The New Plans form requires UI fixes.
SW-030 | Invoice Page | New Invoice Form Requires Fixes | Medium | To Do | The New Invoice form requires UI improvements.
SW-031 | Dashboard | Manage Button Requires UI Redesign | Medium | To Do | The Manage button requires a new UI to match the intended design.
SW-032 | Edit Shop | City Field Contains Unnecessary Clear Icon | Low | To Do | The City field on the Edit Shop form displays an unnecessary cross/clear icon that should be removed.
SW-033 | Shop | Account Status Buttons Not Functioning Properly | High | To Do | The Activate, Suspend, and Archive status buttons do not provide immediate feedback or update the shop status as expected.
SW-034 | Shop | Missing Notification After Account Status Change | Medium | To Do | No success notification or confirmation is displayed after changing a shop account status.
SW-035 | Shop | Status Action Buttons Have High Interaction Latency | High | To Do | The Activate, Suspend, and Archive buttons have noticeable interaction latency and require optimization.
SW-036 | Shops Page | Non-Functional Shop Name Search | Medium | To Do | The "Search by Shop Name" field in the Shop Location section does not perform a search and should either be fixed or removed.
SW-037 | New Shop Form | Phone Field Color Changes Incorrectly | Low | To Do | The Phone Number field turns white when focused and changes back after a number is entered, creating inconsistent styling.
SW-038 | New Shop Form | Password Visibility and Validation Display Issue | Medium | To Do | The password field becomes white and difficult to read when the entered password does not meet the required password criteria.
SW-039 | Shop Page | Status Editable in View Mode | Medium | To Do | The View option allows users to modify the shop status even though a separate Edit option exists. The View page should be read-only.
SW-040 | Shop Page | Card Displays Incorrect Account Status | High | To Do | The shop card displays an incorrect account status that does not match the actual account state.
SW-041 | Plans Page | CRUD Functionality Not Implemented | High | To Do | The Plans page does not support complete Create, Read, Update, and Delete operations.
SW-042 | Designer Page | Form Clears Email and Username While Retaining Password | High | To Do | When an existing email or username is entered, the corresponding fields are cleared while the password remains populated. Form data should be handled consistently after duplicate validation.
SW-043 | Designer Page | Status Control UI Requires Improvement | Medium | To Do | The Designer status control requires UI improvements, clearer visual feedback, and better alignment.
SW-044 | Designer Page | Phone Number Field Has No Input Limit | Medium | To Do | The Designer Phone Number field does not enforce a maximum character or digit limit.
SW-045 | Designer Page | Edit Form Cannot Be Submitted | High | To Do | The Designer Edit form cannot be successfully submitted after changes are made.
SW-046 | Designer Page | Edit Form Displays Error Message | High | To Do | The Designer Edit form displays an unexpected error during the update process.
SW-047 | Sign In | Password Visibility Toggle Icon Not Visible | Medium | To Do | The password visibility eye icon is not visible after entering a password on the Admin Sign In form.
SW-048 | Sign In | Remove Arrow Icon from Sign In Button | Low | To Do | The Sign In button contains an unnecessary arrow icon that should be removed.
SW-049 | Card Template Page | Create Template Button Displayed on Multiple Steps | Medium | To Do | The Create Template button appears on the Type and Design steps. It should only be displayed on the final Info step.
SW-050 | Card Template Design Step | Incorrect Template Name Validation Error | High | To Do | A Template Name validation error appears on the Design step even though the name has already been entered and the current page contains no Template Name field.
SW-051 | Statistics | Statistics Cards Display Incorrect Metrics | High | To Do | The statistics cards display incorrect metrics that do not match the actual system data.
SW-052 | Statistics | Main Bar Chart Unavailable | High | To Do | The main statistics bar chart does not load or render.
SW-053 | Agent Management | Phone Number Requires Validation Limit | Medium | To Do | The Agent Phone Number field does not enforce an appropriate maximum digit/character limit.
SW-054 | Request Handling | Status Column Does Not Refresh | High | To Do | After accepting or rejecting a request, the status shown in the table does not refresh or update immediately.
SW-055 | Invoice Page | Invoice Table UI Issues | Medium | To Do | The Invoice table contains UI alignment and rendering issues affecting readability.
SW-056 | Designer Form | Validation Error Does Not Clear | Medium | To Do | When a Designer form error is corrected, the validation error message remains visible instead of disappearing.
SW-057 | New Designer Form | Input Field Styling Inconsistent | Low | To Do | The Full Name and Email fields change color when text is entered while other fields retain different styling. --- ## OWNER

## Owner Portal
Bug ID | Module/Area | Title | Priority | Status | Description
SW-058 | Dashboard | Poor Color Contrast | Medium | To Do | Dashboard colors are overly blended, reducing readability and visual hierarchy.
SW-059 | Customers Page | New Card Form UI Issues | Medium | To Do | The Plus/Issue button opens a New Card form containing UI inconsistencies.
SW-060 | Activity Page | Heading and Layout Issues | Medium | To Do | The Activity heading, typography, and overall layout require UI improvements.
SW-061 | Notifications Page | Layout and Color Issues | Medium | To Do | The Notifications page lacks proper margins/padding and has poor color contrast.
SW-062 | History Page | Layout and Color Issues | Medium | To Do | The History page lacks proper spacing and has poor color contrast.
SW-063 | Card Templates Page | New Template Button Needs Adjustment | Medium | To Do | The New Template button requires UI adjustments.
SW-064 | Staff Page | Incorrect Section Order | Low | To Do | Staff sections should appear in the order Add Form → Owner Table → Manager Table → Scanner Table.
SW-065 | Settings Page | Card Defaults Module Not Working | High | To Do | The Card Defaults module is non-functional.
SW-066 | Open Scanner Page | Non-Functional Black Screen | High | To Do | The Open Scanner page displays a black screen and is non-functional.
SW-067 | Forget Password | Password Visibility Toggle Controls Multiple Fields | High | To Do | Clicking the eye icon for New Password also reveals the Confirm Password field. Each password field should have an independent visibility toggle.
SW-068 | Request Access Form | Missing Validation Messages | Medium | To Do | No validation message is displayed when City, Business Type, or Location is left empty.
SW-069 | Back to Home | UI and Functionality Issues | Medium | To Do | The Back to Home button requires UI and functionality improvements.
SW-070 | Add Staff | Password Remains Visible After Staff Creation | High | To Do | After successfully adding a staff member, the entered password remains visible on the screen. Sensitive information should be cleared after successful submission.
SW-071 | Account | Remains Logged In After Suspension or Archive | High | To Do | When an admin suspends or archives an owner account, the owner remains logged in and can continue accessing the system.
SW-072 | Archived Account | Incorrect Error Message | High | To Do | An incorrect message is displayed for an archived account. Expected: "Shop archived by admin. Please contact admin."
SW-073 | Add Staff | Sensitive Data Remains After Submission | High | To Do | After successfully adding staff, the entered email remains in the Email field and the staff password appears in the Admin Password field.
SW-074 | Request Access Form | Missing Map Selection Validation | Medium | To Do | No validation message is displayed when a required map location has not been selected.
SW-075 | Request Access Form | Remove Back to Sign In Button | Low | To Do | The Back to Sign In button in the top-right corner should be removed.
SW-076 | Scanner Page | No Navigation Back to Main Website | Medium | To Do | There is no visible option to return to the main website from the Scanner page.
SW-077 | Account Suspended Page | Remove Sign Out Button | Low | To Do | The Sign Out button on the Account Suspended page is unnecessary and should be removed.
SW-078 | Suspended Account | Does Not Logout Immediately | High | To Do | When an active account is suspended while the owner is browsing, the account remains active until the user navigates to another page.
SW-079 | Suspended Account | Protected Route Redirect Fails | High | To Do | Attempting to access protected routes such as /dashboard or /settings after suspension results in a 404 page instead of redirecting to /account-suspended.
SW-080 | Account Suspended Page | UI Improvements Required | Medium | To Do | The Account Suspended page requires improvements to layout, spacing, typography, button placement, and visual hierarchy.
SW-081 | Sidebar | Text Overflow Outside Navigation Panel | Medium | To Do | Sidebar text extends outside the navigation panel. Text should remain contained within the sidebar.
SW-082 | Subscription & Trial Expiry Banner | Contact Button Redirects Incorrectly | Medium | To Do | The Contact button displayed when a subscription or trial is approaching expiry redirects incorrectly or does not follow the intended navigation flow.
SW-083 | Card Template Page | Logo Upload Returns Unexpected Error | High | To Do | Uploading a card template logo results in an unexpected error.
SW-084 | Card Template Page | Validation Error Does Not Clear After Correction | Medium | To Do | A validation error remains visible even after the user starts correcting the invalid field.
SW-085 | Card Template Design Step | Incorrect Template Name Validation Error | High | To Do | A Template Name error appears on the Design step even though the name has already been entered and there is no Template Name field on that step.
SW-086 | Sign In | Remove Arrow Icon from Sign In Button | Low | To Do | The Owner Sign In button displays an unnecessary arrow icon.
SW-087 | Card Template | Remove Arrow Icons from Navigation Buttons | Low | To Do | Back and Next buttons on the Design and Info steps display unnecessary arrow icons.
SW-088 | Card Template | Validation Messages Not Following Field Order | Medium | To Do | Validation messages for empty fields do not appear according to the sequence of the form fields.
SW-089 | Profile | Separate New Password and Confirm Password Fields Required | High | To Do | Password change functionality should provide separate New Password and Confirm Password fields.
SW-090 | Customer Page | Require Account Password Before Adding Customer | High | To Do | Clicking Add should open a security modal requesting the owner's account password before allowing a new customer to be added.
SW-091 | Customer Page | Add Direct Customer Notification Option | Medium | To Do | The Customer page should provide an option to send a notification directly to a selected customer.
SW-092 | Card Template | First Terms & Conditions Point Not Displayed | High | To Do | "Receive one stamp with every purchase" is not correctly delivered/displayed.
SW-093 | Card Template | Second Terms & Conditions Point Not Displayed | High | To Do | "Collect stamps to earn rewards" is not correctly delivered/displayed.
SW-094 | Card Template | Third Terms & Conditions Point Not Displayed | High | To Do | "The card, stamps, and rewards do not expire" is not correctly delivered/displayed.
SW-095 | Card Template | Fourth Terms & Conditions Point Not Displayed | High | To Do | "Stamps and rewards cannot be redeemed, returned, exchanged, transferred, or purchased for cash" is not correctly delivered/displayed.
SW-096 | Card Template | Fifth Terms & Conditions Point Not Displayed | High | To Do | "Cards are non-transferable and cannot be combined with other cards" is not correctly delivered/displayed.
SW-097 | Card Template | Sixth Terms & Conditions Point Not Displayed | High | To Do | "The company reserves the right to refuse service" is not correctly delivered/displayed.
SW-098 | Card Template | Terms & Conditions Not Fully Delivered | High | To Do | All configured Terms & Conditions must be saved, retrieved, and displayed completely and in the correct order.
SW-099 | Add Staff Page | Phone Number Field UI Inconsistent | Low | To Do | The Phone Number field has a blue style that is inconsistent with the remaining fields.
SW-100 | Activity Page | Replace "Stamp" with "SIKKA" | Low | To Do | The Action column displays "Stamp" and should use "SIKKA" instead.
SW-101 | Dashboard | Lapsing Outcome Functionality Pending Verification | Medium | To Do | The Lapsing Outcome functionality could not be fully validated because the required data scenario could not be confirmed.
SW-102 | Staff Management | Suspend Option Non-Functional | High | To Do | The Suspend option for staff members does not perform the expected operation.
SW-103 | Profile | Card Default Settings Not Applied | High | To Do | Card Default configuration changes are not saved or applied.
SW-104 | Profile | Location Search Not Working | Medium | To Do | Location/map address search does not return the expected results.
SW-105 | Profile | Owner Profile Screen Non-Functional | High | To Do | The dedicated Owner Profile screen is broken and throws an error.
SW-106 | Profile Navigation | Profile Option Opens Settings Page | Medium | To Do | Selecting Profile redirects the user to the Settings page instead of the Owner Profile page.
SW-107 | Notifications | Incorrect Wallet App Validation Error | High | To Do | When sending a notification, the system reports that the customer does not have the wallet app even though the customer has it. --- ## MAIN WEBSITE

## Main Website
Bug ID | Module/Area | Title | Priority | Status | Description
SW-108 | Homepage | MPT Cards Counter Should Be Replaced with Image | Medium | To Do | The MPT Cards section displays a shop counter such as 614/800. The counter should be replaced with the intended image.
SW-109 | Homepage | Missing Images in "From Scan to Reward" | High | To Do | Images are missing for Merchant Dashboard, Card Design, Sikka Activity, and Sikka Wallet.
SW-110 | Homepage | Missing Images in "Built For Everyone" | High | To Do | Images are missing for the Shopkeepers and For Your Customers counter blocks.
SW-111 | Homepage | Talk to Sales Button UI Needs Improvement | Medium | To Do | The Talk to Sales button in the Ready to Start section requires UI/UX improvements.
SW-112 | Homepage | MPT Cards Alignment Incorrect | Medium | To Do | MPT cards should display the icon on the left and the number/counter on the right.
SW-113 | For Shop Page | Bland Color Palette | Low | To Do | The overall color palette appears dull and requires visual polish to better match the brand.
SW-114 | Pricing Page | Bland Color Palette | Low | To Do | The Pricing page has no functional issue, but the colors appear bland and require visual enhancement.
SW-115 | Demo Page | Static Demo | High | To Do | The Demo section is static instead of being connected to the actual interactive/live demo flow.
SW-116 | About Page | Remove Arrowhead from Talk to Sales Button | Low | To Do | The Talk to Sales button contains a straight line with an arrowhead. The arrowhead should be removed.
SW-117 | Header | Remove Arrowhead from Get in Touch Button | Low | To Do | The Get in Touch button in the top navigation contains an unnecessary arrowhead that should be removed.
SW-118 | Footer | Footer Size Too Large | Low | To Do | The footer is too broad/tall across the website and should be reduced for better proportions.
SW-119 | Global | Website Not Responsive | High | To Do | The website is not properly responsive across different screen sizes. Multiple pages have broken layouts, spacing, and alignment across breakpoints.
SW-120 | Homepage | Hamburger Menu Font Size Too Large | Medium | To Do | Text inside the hamburger menu uses an excessively large font size and requires adjustment.
SW-121 | Homepage | Talk to Sales Button Size Needs Adjustment | Low | To Do | The Talk to Sales button in the Ready to Start section requires size and spacing adjustments.
SW-122 | Homepage | Remove Arrow from Hamburger Menu Get in Touch Button | Low | To Do | The Get in Touch button inside the hamburger menu displays an unnecessary arrow that should be removed.

## Loyal Sikka App
Bug ID | Module/Area | Title | Priority | Status | Description
LSA-001 | Signup Form | Signup Form / Phone Number Field Validation | Medium | To Do | The phone number field does not have a maximum character limit. Additionally, the +92 country code does not appear by default and only becomes visible after selecting the field.
LSA-002 | Login Flow | Login Flow / Rejected Request Status Not Displayed | High | To Do | When a user's access request is rejected by the admin, the user does not receive an appropriate popup/message when attempting to log in. The system should clearly indicate that the request was rejected or denied by the admin.
LSA-003 | Login Form | Login Form / Empty Fields Error Message | High | To Do | When the user clicks Sign In with both email and password fields empty, the system displays an incorrect error message. It should display "Please enter email and password."
LSA-004 | Login Form | Login Form / Invalid Email Validation | High | To Do | When an invalid email format such as abcdghhhg is entered, the system does not display the correct validation message. It should display "Please enter a valid email address."
LSA-005 | Forgot Password | Forgot Password / Non-Existent Email Validation | High | To Do | When a user enters an email address that does not exist in the system on the Forgot Password screen, the appropriate error message is not displayed. The system should indicate that the email does not exist.
LSA-006 | Password Field | Password Field / Missing Password Security Requirements | High | To Do | The password field does not enforce the required security requirements. The password should have a 10-character limit/requirement and support the required combination of alphanumeric characters and symbols.
LSA-007 | Request Access Form | Request Access Form / Empty Form Validation | High | To Do | Submitting the Request Access form with all required fields empty does not display the correct validation message. It should display "Please fill out all required fields before submitting."
LSA-008 | Request Access Form | Request Access Form / Field-Level Validation Messages | High | To Do | The Request Access form does not provide clear field-level validation. Each missing required field should display its own relevant message, such as "Please select a plan" and "Please enter cafe name."
LSA-009 | Request Access Form | Request Access Form / Validation Errors Do Not Clear on Input | Medium | To Do | When a validation error is displayed for an empty field, the error remains visible even after the user starts entering valid information. The error should disappear once the field becomes valid rather than remaining until Send Request is clicked again.
LSA-010 | Shop Suspension | Shop Suspension / Active Session Not Terminated | High | To Do | When a shop is suspended by the admin while the shop user is already logged in, the active session remains accessible. The system should force the user to log out and display an appropriate "Shop Suspended" message.
LSA-011 | Shop Archive | Shop Archive / Active Session Not Terminated | High | To Do | When a shop is archived by the admin while the shop user is already logged in, the active session remains accessible. The system should force the user to log out and display an appropriate "Shop Archived" message.
LSA-012 | Login Form | Login Form / Irrelevant Error Message for Invalid Login | High | To Do | When invalid login credentials are entered, the system displays the irrelevant generic message "Operation Failed" instead of a meaningful authentication error such as "Invalid email or password."
LSA-013 | Manager | Manager / Customer Screen / Missing Back Navigation Icon | Medium | To Do | The Customer screen for the Manager role does not have a back navigation icon at the top, making navigation back to the previous screen difficult.
LSA-014 | Manager | Manager / Customer Screen / Issue Button UI Not Proper | Medium | To Do | The Issue button on the Customer screen is not displayed properly and does not follow the intended UI design in terms of styling, alignment, spacing, and appearance.
LSA-015 | Manager | Manager / Customer Screen / Prefilled Text Appears as User Input | Medium | To Do | When the Manager clicks the Issue button, the prefilled/default text in the form appears in black, making it look like user-entered information rather than placeholder or default text.
LSA-016 | Manager | Manager / Customer Screen / Incorrect Edit Screen Title | Low | To Do | The title displayed when editing a customer from the Manager's Customer screen is incorrect or misleading. It should clearly indicate the current action, such as "Edit Customer."
LSA-017 | Account Archive | Account Archive / Incorrect Suspension Message | High | To Do | When a Shop Owner, Manager, or Scanner account is archived, the application displays "Account Suspended" instead of an archive-specific message. The system should display "Account Archived" or an equivalent message.
LSA-018 | Manager | Manager / Customer Card / Unnecessary Top Spacing on Issue Screen | Medium | To Do | When the Manager clicks the Issue button from a Customer Card, unnecessary empty space appears at the top of the Issue screen. The dead space should be removed.
LSA-019 | Manager | Manager / Customer Card / Required Sikka Field Misalignment | Medium | To Do | On the Issue form, the Required Sikka field is not properly aligned with the Rewards field. Both fields should have consistent alignment and spacing.
LSA-020 | Manager | Manager / Customer Card / Missing Validation on Empty Issue Form | High | To Do | When the Manager clicks the Issue button and submits the form without entering any required information, no validation errors are generated. Required fields should display appropriate field-level error messages.
LSA-021 | Manager | Manager / Customer Card / Issue Button Click Feedback Not Prominent | Low | To Do | The visual feedback when clicking the Issue button is not sufficiently noticeable. The interaction should provide clearer visual feedback so the user can easily identify that the button has been activated.
LSA-022 | Change Password | Change Password / Mismatched Password Fields Not Highlighted | High | To Do | When the New Password and Confirm Password values do not match, the affected fields are not highlighted. The relevant fields should be visually highlighted along with the validation message.
LSA-023 | Change Password | Change Password / Invalid Current Password Not Highlighted | High | To Do | When an incorrect Current Password is entered, the Current Password field is not highlighted. The field should be highlighted and display an appropriate validation message.
LSA-024 | Change Password | Change Password / Validation Errors Do Not Clear on Input | Medium | To Do | Change Password validation errors remain visible even after the user starts correcting the input. The relevant error should disappear once the input becomes valid.
LSA-025 | Change Password | Change Password / Password Visibility Toggle Affects Multiple Fields | High | To Do | Using the password visibility toggle on one password field also changes the visibility state of another password field. Each password field should have an independent visibility toggle.
LSA-026 | Profile Edit | Profile Edit / Missing Field-Level Validation for Mandatory Fields | High | To Do | When mandatory fields are empty during profile editing, the system does not properly guide the user. Errors should appear beneath the relevant fields, the fields should be highlighted, and the user should be taken/focused to the affected field.
LSA-027 | Profile Edit | Profile Edit / Empty City and Business Type Fields Can Be Submitted | High | To Do | When the City and Business Type fields are empty, the profile form can still be submitted without generating validation errors. Previous data may also continue to appear outside the form, resulting in inconsistent data presentation.
LSA-028 | Profile Edit | Profile Edit / Incorrect City Special-Character Validation | Medium | To Do | When special characters are entered in the City field, the system displays an incorrect validation message. The field should provide an accurate validation message based on the allowed input format.
LSA-029 | Profile Edit | Profile Edit / Missing Character Limits and UI Improvements | Medium | To Do | The Profile Edit screen requires UI refinement and appropriate character limits for applicable input fields to prevent excessive or invalid data entry.
LSA-030 | Sign-In Screen | Sign-In Screen / Incorrect Password Placeholder Text | Low | To Do | The password field placeholder text on the Sign-In screen should be changed to "ENTER YOUR PASSWORD".
LSA-031 | Profile Edit | Profile Edit / Selected City Not Displayed | High | To Do | On the Profile Edit screen, the City field appears empty even when a city has already been selected or saved. The selected city should be displayed correctly.
LSA-032 | Profile Edit | Profile Edit / City Search Text Not Visible | High | To Do | When the user types a city name into the City field to search, the entered text does not appear in the field. The search text should be visible while the user is typing.
LSA-033 | Dashboard | Dashboard / Overview / Incorrect First Card Title | Low | To Do | The title of the first card on the Dashboard Overview screen is incorrect. The correct title should be "Card Templates."
LSA-034 | Change Password | Change Password / Incorrect Validation Priority for Current Password | High | To Do | When the Current Password is intentionally incorrect and the New Password simultaneously fails the character requirement, the system displays the New Password character-limit error first. The system should validate the Current Password first and display the incorrect-current-password error before proceeding with other password validations.
LSA-035 | Profile Edit | Profile Edit / Validation Error Messages Do Not Clear on Input | Medium | To Do | When a validation error is displayed on a Profile Edit field, the error remains visible after the user starts entering valid information. The error should automatically disappear once the field becomes valid.
LSA-036 | Settings | Settings / City Information Missing in Shop Profile Data | High | To Do | The City information is missing from the Shop Profile data displayed under Settings. The saved city should be displayed correctly as part of the shop profile information.
LSA-037 | Access Request | Access Request / Plan Dropdown Positioning Issue | Medium | To Do | The Plan dropdown on the Access Request form is not positioned/aligned correctly when opened and appears over the Plan field. The dropdown should open with proper positioning and alignment.
LSA-038 | Dashboard | Dashboard / "Good Morning" Greeting Too Small | Low | To Do | The "Good Morning" greeting on the dashboard appears too small. Its font size and styling should be increased appropriately to make the greeting more prominent.
LSA-039 | Scanner Screen | Scanner Screen / Popup Message Placement Issue | Medium | To Do | The popup message on the Scanner screen is not positioned correctly, resulting in a poor layout. Its placement should be adjusted according to the intended UI design.
LSA-040 | Dashboard | Dashboard / Stamps Today and Redemptions Cards Not Clickable | Medium | To Do | The Stamps Today and Redemptions dashboard cards are not clickable and do not lead to their respective screens. The cards should be interactive and navigate to the appropriate leading/detail screens.
LSA-041 | Manager | Manager / Customer Screen / Incorrect Customer Sequence | Medium | To Do | Customers on the Manager Customer screen are displayed in an incorrect sequence. The customer list should follow the intended sorting/order requirements.
LSA-042 | Manager | Manager / Customer Screen / Unnecessary Back Navigation Arrow | Low | To Do | The back navigation arrow on the Manager Customer screen should be removed as it is not required for the intended navigation flow.
LSA-043 | Scanner Role | Scanner Role / Scanner Functionality Not Working | High | To Do | The Scanner functionality is not working for the Scanner role, preventing the user from performing the required scanning operation.
LSA-044 | Scanner Role | Scanner Role / Redeem Screen Displays Unnecessary Scanner Box | Medium | To Do | The Redeem screen for the Scanner role displays a scanner box unnecessarily. The scanner component should only be displayed where it is required.
LSA-045 | Manager & Owner | Manager & Owner / Customer Detail Page / Unnecessary Top Spacing | Medium | To Do | The Customer Detail page for both Manager and Owner roles contains unnecessary empty space at the top of the screen. The dead space should be removed to improve layout consistency.
LSA-046 | Dashboard | Dashboard / Total Earnings Not Displayed | High | To Do | The Total Earnings value is not displayed on the app dashboard. The dashboard should correctly display the total earnings information.
LSA-047 | Redeem Points Screen | Redeem Points Screen / UI and Functionality Requires Improvement | Medium | To Do | The Redeem Points screen requires overall UI and usability improvements. The screen should be refined in terms of layout, spacing, alignment, visual presentation, and functionality to meet the intended application design.